## plan
|  |  | Task Owner | Phase 1 | [7 empty] | Phase 2
|  |  |  | Week 1-1 | 1-2 | 1-3 | 1-4 | 1-5 | 1-6 | 1-7 | 1-8 | Week 2-1 | 2-2 | 2-3 | 2-4 | 2-5 | 2-6 | 2-7 | 2-8
Task Id | Task Description
1 | Project definition | bar: Phase 1 1-2; Phase 1 1-8
1-1 |  | - confirmation of requirements | TS/ASD | bar: Phase 1 1-2
1-2 |  | - scope definition | All
2 | Data pre-processing
2-1 |  | - initial review & exploration | bar: Phase 1 Week 1-1 to Phase 1 1-3
2-2 |  | - top-level categorisation | bar: Phase 1 1-3
2-3 |  | - cleaning & enrichment | bar: Phase 1 Week 1-1 to Phase 1 1-3
3 | Detailed exploratory analysis & modeling
3-1 |  | - complete data categorisation - by and within grade type | ASD | bar: Phase 1 1-3 to Phase 1 1-4
3-2 |  | - document data structure and content, along with key changes in data/awards/reporting | bar: Phase 1 1-2 to Phase 1 1-4
3-3 |  | - define basic statistical calculations, other indicators and metrics to be implemented | ASD | bar: Phase 1 1-3 to Phase 1 1-5; Phase 1 1-7
3-4 |  | - identify (any) additional advanced data modeling | bar: Phase 1 1-7 to Phase 1 1-8
3-5 |  | - initial scenario-based UI design | ASD | bar: Phase 1 1-4 to Phase 1 1-5
3-6 |  | - identify & explore visualisation techniques | All volunteers | bar: Phase 1 1-4 to Phase 1 1-6
4 | Stage 1 reporting
4-1 |  | - statistical and visual analysis and results | ASD | bar: Phase 1 1-5 to Phase 1 1-7
4-2 |  | - evaluation & validation of initial results & design | ASD | bar: Phase 1 1-2 to Phase 1 1-8
5 | Requirements review & final UI design
5-1 |  | - additional data exploration | bar: Phase 1 1-6 to Phase 1 1-8
5-2 |  | - identification of other key end user characteristics | bar: Phase 1 1-6
5-3 |  | - development of storyline | ASD | bar: Phase 1 1-6 to Phase 1 1-7
5-4 |  | - tool exploration | All volunteers | bar: Phase 1 1-5 to Phase 1 1-6
6 | Deployment - Phase 1 Prototype | bar: Phase 1 1-8
6-1 |  | - project review
7 | Finalisation of requirements and design
8 | Construction of UI
9 | Construction of visualisations
10 | Development of analytics support
10-1 |  | - analytics functionality
10-2 |  | - reporting functionality
11 | Evaluation
12 | Presentation of results - reporting & exploration
13 | Final evaluation
14 | Deployment
15 | Handover

## deliverables
No. | Due | Deliverables
1 | S1-W | Data store & documentation - incl. errors, assumptions and key changes to awards
2 |  | Map of requirements to metrics
3 |  | Initial results & insight gained
4 |  | UI design & user scenarios
5 | S1-W8 | Deployment v1 - mainly static visualisation & reporting
6 | S2-W | Deployment v2 - interactive, web-based visualisation

## task_owners
Initials | Name | Hours/Wk | Notes
TS | Toni Scullion | N/A
ASD | Aba-Sah Dadzie | 12 | hours may go down to 8
MS | Matthew Shedden | 6
MP | Marta Pasikowska |  | Code Clan grad mentee